## How to Use
DON'T CHASE IT
Project Manager Trackers
Companion to the book by J. Micah Covey · dontchaseit.com
How this works
Five logs, one per tab. Each one exists because the book argues a project loses money without it. Fill in the pale yellow cells. White cells calculate on their own — don't type over them.
TAB | WHAT IT'S FOR
RFI Log | Ages every open RFI against your contract review period — not against nothing. Chapter 9.
Submittal Log | Tracks turnaround and forces a stated basis on every rejection. Chapter 9.
Substitution Register | Records who represented suitability on each approved alternate. Chapter 9.
Decision Log | Open decisions with an owner, a needed-by date, and the consequence of missing it. Chapter 3.
Contract Clauses | The five provisions that decide who pays, summarized for your specific contract. Chapter 4.
Set this first
Contract review period (days) | 14
Both the RFI and Submittal tabs age against this number. Find it in your contract — it is not always 14.

## RFI Log
RFI Log
Aging is measured against the contract review period set on the How to Use tab.
RFI # | Subject | CSI Div | Submitted to | Date submitted | Response received | Days open | Past review period | Work impacted | Response changed scope? | PCO opened | Notes
RFI-014 | Ceiling height conflict at Grid D — RCP vs. duct main | 23 00 00 | C. Nakamura | 2026-07-19 |  | 22 | YES — 8 days over | Level 2 mech rough-in | Yes — routing revised | PCO-006 | Response directs new routing. Priced as change.
↑ Example row — delete before use. Yellow cells are yours to fill in; white cells calculate themselves.
Formulas:
Days open = IF([Date submitted]="","",IF([Response received]="",TODAY()-[Date submitted],[Response received]-[Date submitted]))

## Submittal Log
Submittal Log
A rejection without a cited spec section or code provision is a rejection you cannot defend.
Submittal # | Package | CSI Div | Subcontractor | Sent to reviewer | Returned | Days in review | Past review period | Result | Basis cited | Rejection # | Procurement date at risk | Notes
SUB-031 | Curtain wall shop drawings | 08 44 00 | LV Glass & Glazing | 2026-07-10 |  | 31 | YES — 17 days over | Revise and resubmit | Spec 08 44 00 §2.3.B — thermal break not shown | 2 | 2026-08-19 | Second rejection. First review did not raise this. Impact claim exposure.
↑ Example row — delete before use. Yellow cells are yours to fill in; white cells calculate themselves.
Formulas:
Days in review = IF([Sent to reviewer]="","",IF([Returned]="",TODAY()-[Sent to reviewer],[Returned]-[Sent to reviewer]))

## Substitution Register
Substitution Register
If this sheet cannot say who vouched for suitability, that question gets decided by whoever argues better.
Sub # | Specified product | Proposed alternate | CSI Div | Requested by | Voluntary or directed | Who represented suitability | Approval language | Date approved | Cost impact | Risk sits with | Notes
SUBST-004 | Specified: Halsey 3000 series sealant | Proposed: Meridian XT-40 | 07 92 00 | Apex Concrete | Voluntary (sub proposed) | Apex Concrete — written rep 4/18 | Approved for general conformance only | 2026-07-01 | -4200 | Subcontractor | Sub proposed for availability. Suitability rep in their letter, filed.
↑ Example row — delete before use. Yellow cells are yours to fill in; white cells calculate themselves.

## Decision Log
Decision Log
A decision with a date and a stated consequence is much harder to defer than one without.
# | Decision required | Owner | Needed by | Days remaining | Consequence if late | Status | Date closed | Notes
1 | Finish selection for corridor wall base — owner has three options outstanding | M. Reyes (Owner) | 2026-08-16 | 6 | Div 09 procurement misses the buy window; 3-week lead becomes 7 | Open |  | Raised twice in OAC. Escalate Friday if still open.
↑ Example row — delete before use. Yellow cells are yours to fill in; white cells calculate themselves.
Formulas:
Days remaining = IF([Needed by]="","",IF([Status]="Closed","",[Needed by]-TODAY()))

## Contract Clauses
The Five Clauses That Decide Who Pays
Fill this out at the start of every project. Keep it where you can reach it in a meeting.
Project | Riviera Commons (example — replace)
Contract form | AIA A201 General Conditions
Clause | Section # | What it says on THIS project | Where it bites
Notice | 3.7.4 | Written notice, promptly and before the condition is disturbed; no later than 14 days after first observance. | Late notice defeats an otherwise sound claim. Clock runs from discovery, not pricing.
Differing site conditions | 3.7.4 | Type I: documents indicated a condition and actual differs materially. Type II: unknown condition of unusual nature. | Type I is the stronger position — you can point at a sheet.
Delay / time extension | 8.3 | Excusable vs. compensable. Check for no-damages-for-delay and concurrent delay language. | Determines whether you get time only, or time and money.
Changes | 7.1 – 7.3 | Who may direct a change, required form, pricing method. Includes the construction change directive mechanism. | A CCD authorizes the work, not the cost. Revise your ROM as it moves.
Order of precedence | 1.2 | Which document governs when the documents conflict. | On a renovation they will conflict. Know the hierarchy before the argument.
Sections shown are AIA A201 references used as an example. Replace with the actual section numbers from your contract.