## Slide 1
WEEK 7
PM MINDSET
HUDDLE SERIES
J. Micah Covey
Author, Don’t Chase It
dontchaseit.com
15 MIN HUDDLE
Capture Before You Release.
The Discipline · Budget Spine · Commitments · Change Capture · Execution
15-Minute Daily Huddle · Monday – Friday

## Slide 2
DAY 1
MONDAY
Capture Before You Release
"No money goes out until the money is captured."
15 MIN HUDDLE | WEEK 7
OPEN 2 min
Think of a time money went out the door on your project before it was fully captured coming in. What did that cost?
FOCUS 8 min
This is the discipline the whole week rests on: nothing gets released until it's been captured. A commitment before work starts. A PCO before cost is incurred. An executed change order before billing. Every dollar that leaves your project should trace back to a dollar you captured first. When that sequence breaks, margin disappears and nobody can tell you where it went.
CHALLENGE 5 min
Find one place on your current project where money is moving without being fully captured. Close that gap today.

## Slide 3
DAY 2
TUESDAY
The Budget Is Your Spine
"A budget built wrong on day one costs you every day after."
15 MIN HUDDLE | WEEK 7
OPEN 2 min
Have you ever inherited a budget set up in a way that made it impossible to track? What did you do?
FOCUS 8 min
Your budget is the financial spine of the project. Cost codes must align to your SOV. Original values must be locked before work starts. Budget modifications must be tracked separately from original scope. When any of those break down, you lose visibility the moment costs move — and you can't capture what you can't see.
CHALLENGE 5 min
Open your current project budget. Confirm cost codes align to your SOV line items. If they don't — that's today's fix.

## Slide 4
DAY 3
WEDNESDAY
Commit Before Work Starts
"An untracked commitment is a liability you don't know you have."
15 MIN HUDDLE | WEEK 7
OPEN 2 min
How many open commitments do you have on your current project right now? Can you answer that without opening the system?
FOCUS 8 min
Every subcontract and purchase order is a commitment — and the moment it's approved, that budget is encumbered. Work that starts without an executed commitment is unencumbered liability: the budget doesn't know it exists, and you have no contractual basis to enforce scope, price, or performance. Capture the commitment before the work starts. Every time.
CHALLENGE 5 min
Run your commitment report today. Identify any commitment that's missing, over budget, or unexecuted. Move one forward.

## Slide 5
DAY 4
THURSDAY
Capture the Change Immediately
"A change you don't document is a change you're paying for yourself."
15 MIN HUDDLE | WEEK 7
OPEN 2 min
Think of a change on a recent project that didn't get captured in time. What did it cost?
FOCUS 8 min
The moment a change occurs — an owner direction, a design revision, a differing site condition — capture it. Open the PCO. Price it if you can, mark it pending if you can't. What you cannot do is wait. A PCO opened the day of the event is defensible. One opened ninety days later is a fight. Capture first, price second, negotiate third.
CHALLENGE 5 min
How many open PCOs do you have right now? Identify one sitting without a cost attached. Price it today.

## Slide 6
DAY 5
FRIDAY
Execute Before You Bill
"A change order that isn't executed isn't money. It's hope."
15 MIN HUDDLE | WEEK 7
OPEN 2 min
What's your average time from PCO to executed change order on your current project? Is that acceptable?
ROUND TABLE 8 min
PCOs without pricing sit. Pricing without owner execution stalls billing. Change orders without signatures don't get paid. The full cycle — capture the change, price it, get it executed, update the SOV, then bill — has to move as fast as the work does. Where is your change log backing up, and what's the bottleneck?
CLOSE 5 min
Capture before you release. Commit before work starts. Document before cost is incurred. Execute before you bill. That sequence is the whole discipline. Break it anywhere and margin walks out the door.